## JAN
FORM NO.: AUT/F/196 Automation One IT w.e.f.: 01.02.2023
Rev :01 Task assignment form
Vendor Name | TCE | For the month of
Name of Developer | JITENDAR KUMAR THAKUR | JAN
Competency
Week. No | Project Name | Task | Planned | Planned End Date | No of Task Assigned | No of Task Completed | No of Days to complete | Check-in/Remarks | Completion %
Start Date
week. No 1 | 1.TSM Khopoli TubeMill Dahboard 2.L2 application Architecture understanding 3.Understand basic operation-Site Visit-CCl and GP | 1.TuebMill Dashboard modification -a.PLC Connectivity status using color code -b.Screen color and control size change as per EPH comments | 1.1/1/2025 2.02/02/2025 3.02/02/2025 | 1.1/1/2025 2.02/02/2025 3.02/02/2025 | .PLC Connectivity status using color code -b.Screen color and control size change as per EPH comments Site Visit Understanding L2 architecture | 2 | 1 |  | 100%
week.No2 | L2 CCL-WIP sticker print -ECL L2 Page wireframe | QR sticker print from L2 | 2025-08-01 | 14/1/2025 | 1.Sticker print |  |  | 06-01-2025 07-01-2025 on leave | 100%
|  |  | 2025-09-01 |  | created a window form for CCL application to dispay coil data in a dialoge .
|  |  | 2025-10-01 |  | created a window form for CCL application to dispay coil data on print button .
week.No 3 | L2 CCL-WIP sticker print -ECL L2 Page wireframe | QR sticker print from L2 | 13/01/2025 |  | written code to generate QR code for Width , Length , Thikness
|  |  | 14/01/2025 |  | worked on CCL application to generate coil data into QR code for scan using machin
|  |  | 15/01/2025 |  | Worked on code to change the degine on sticker and visted ccl plant
|  |  | 16/01/2025 |  | change QR resolution to scan the QR code exactly and testing done
|  |  | 17/01/2025 |  | Added unit into all value like thikness,width,Length etc and visted ccl plant for testing of sticker
100%
week.No 4 | L2 GP-WIP sticker print and tube mill application -ECL L2 Page wireframe | QR sticker print from L2 and chage the tube mill dashbord | 20/01/2025 |  | Added date time with formate in CCL sticker and worked on tubemill application to fetch data into Advance page in detail view from OUTPUT table
|  |  | 21/01/2025 |  | worked on tubemill application into Advance page in detail view background-color change of row according to Error aslo Added symbol for each graph according to its status.
|  |  | 22/01/2025 |  | Worked on tubemill application into Advance page in chart Added symbol for voltage and current indivisually and also added split delayed page in GP2 application
|  |  | 23/01/2025 |  | Worked on GP2 sticker form and binded data with form in stikcer
|  |  | 24/01/2025 |  | worked on CCL application on splite delay page fetched data from databse using query and splite delayed data.Went to
Week No 5 | CCL Enhancement 1.Auto sticker print 2.Animation for active Uncoiler in the tracking page 3.Add filter inbetween dat and shift for the summary report GP Enhancement 1.Delay Split feature |  | 27/01/2025 |  | . Went to Power plant and created a view for IONDATA_LOG2 table also created an user to access data.
|  |  | 28/01/2025 |  | .Went to Power plant to check data and for IONDATA_LOG2 testing
|  |  | 29/01/2025 |  | .Worked on Tubmill application to fetch data in detail tab on show button click
|  |  | 30/01/2025 |  | .Worked on CCL Application to display sticker as auto popup after coil completion
|  |  | 31/01/2025 |  | Worked on TubeMill application to stop data fetching on shift changing

## FEB
FORM NO.: AUT/F/196 Automation One IT w.e.f.: 01.02.2023
Rev :01 Task assignment form
Vendor Name | TCE | For the month of
Name of Developer | JITENDAR KUMAR THAKUR | FEB
Competency
Week. No | Project Name | Task | Planned | Planned End Date | No of Task Assigned | No of Task Completed | No of Days to complete | Check-in/Remarks | Completion %
Start Date
Week No. 1 | GP Application |  | 2025-03-02 |  | Tube mill application error on Chart solution
|  |  | 2025-04-02 |  | GP Return Planning form creation in PDI and PDO hold request option.
|  |  | 2025-05-02 |  | coil running in CCL application in Lavel 2
|  |  | 2025-06-02 |  | GP menually PDO creation
|  |  | 2025-07-02 |  | Added a feature to auto Popup for sticker in GP application.
Week No. 2 | CCL Application |  | 2025-10-02 |  | Added code to run recoiler design(animation) on every second according UNcoiler machine if the speed value will zero then recoiler design will stop.
|  |  | 2025-11-02 |  | In CCL application added code to run UNcoiler according to singnal data that which coil is running .
|  |  | 2025-12-02 |  | In CCL application in PDI form two Textbox to understand the person name and reason added Manually_by and menually_reason and created procedure to insert data into table.
|  |  | 13/2/2025 |  | In CCL aaplication worked to run Recoiler design shape according to real time machine status .
|  |  | 14/2/2025 |  | Visted Tubmill plant to check status of PIms server also visted CCL and GP plant to understand the GR issue in the aaplication and resolve the issue and in CCL plant understand the other requirement of user.
| EMS application |  | 17/2/2025 |  | Visted CCL plant to analysis the issue in CCL application in advance module PDO was not generating properly.
|  |  | 18/2/2025 |  | In EMS application created a HMI to display electricity consumtion data also displayed running status
|  |  | 19/2/2025 |  | Worked on coding part for EMS application to fetch data from sql database using ado.net .
|  |  | 20/2/2025 |  | Created graph to display chart for machine data in EMS application
|  |  | 21/2/2025 |  | Added code to export excel of Machine data from Table which is displayed in screen.
Week No. 1 | GP Application |  | 24/2/2025 |  | Worked on EMS application to display graph in page according to Mill data and created table in to Pims database to recieve data from EMS database . also added in EMS applicattion dropdownlist to select data according to mill .
|  |  | 25/2/2025 |  | Worked on EMS application to display Current(KWH) Consume by MILL in graph added timeStamp as X axis in graph .
|  |  | 26/2/2025 |  | Worked on EMS application to display chart responsive and time in X-axis wrote new code to fetch data from Pims tabale and work on designing of chart.
|  |  | 27/2/2025 |  | Changed code to show date and time in X -axis only below of KWH data shown in chart
|  |  | 28/2/2025 |  | Visited plant