## Sheet1
FORM NO.: AUT/F/196 Automation One IT w.e.f.: 01.02.2023
Rev :01 Task assignment form
Vendor Name | TCE | For the month of
Name of Developer | JITENDAR KUMAR THAKUR | FEB
Competency
Week. No | Project Name | Task | Planned | Planned End Date | No of Task Assigned | No of Task Completed | No of Days to complete | Check-in/Remarks | Completion %
Start Date
Week No. 1 | GP Application |  | 2025-03-02 |  | In Tube mill application error was coming on Chart i added solution to resoved it.
|  |  | 2025-04-02 |  | In GP2 Application added Return Planning option in PDI form so that user can Return PDI and PDO hold request option.
|  |  | 2025-05-02 |  | coil running in CCL application in Lavel 2
|  |  | 2025-06-02 |  | GP menually PDO creation
|  |  | 2025-07-02 |  | Added a feature to auto Popup for sticker in GP application.
Week No. 2 | CCL Application |  | 2025-10-02 |  | Added code to run recoiler design(animation) on every second according UNcoiler machine if the speed value will zero then recoiler design will stop.
|  |  | 2025-11-02 |  | In CCL application added code to run UNcoiler according to singnal data that which coil is running .
|  |  | 2025-12-02 |  | In CCL application in PDI form two Textbox to understand the person name and reason added Manually_by and menually_reason and created procedure to insert data into table.
|  |  | 13/2/2025 |  | In CCL aaplication worked to run Recoiler design shape according to real time machine status .
|  |  | 14/2/2025 |  | Visted Tubmill plant to check status of PIms server also visted CCL and GP plant to understand the GR issue in the aaplication and resolve the issue and in CCL plant understand the other requirement of user.
| EMS application |  | 17/2/2025 |  | Visted CCL plant to analysis the issue in CCL application in advance module PDO was not generating properly.
|  |  | 18/2/2025 |  | In EMS application created a HMI to display electricity consumtion data also displayed running status of all feeders.
|  |  | 19/2/2025 |  | Worked on coding part for EMS application to fetch data from sql database using ado.net .
|  |  | 20/2/2025 |  | In the EMS application, a graph has been created to display machine KWH data based on mill selection.
|  |  | 21/2/2025 |  | In the EMS application, code has been added to export an Excel sheet of machine data displayed on the screen, including alerts and running status.
Week No. 1 | EMS Application |  | 24/2/2025 |  | Worked on the EMS application to display a graph on the page based on mill data and created a table in the PIMS database to receive data from the EMS database. Also, added a dropdown list in the EMS application to select data based on the mill.
|  |  | 25/2/2025 |  | Worked on the EMS application to display the current (KWH) consumption by the mill in a graph and added timestamp as the X-axis in the graph.
|  |  | 26/2/2025 |  | Worked on EMS application to display chart responsive and time in X-axis wrote new code to fetch data from Pims tabale and work on designing of chart.
|  |  | 27/2/2025 |  | In ems Ap X-axis on the chart added code to show date and time only below of KWH data shown in chart .
|  |  | 28/2/2025 |  | Visited plant GP plan to all process about coil schedule to PDO generation . also